## Activities
Activity | Area | Start Date | End Date | SortOrder
Auth Service v2 | Engineering | 2026-01-01 | 2026-09-30 | 0
Data Pipeline Refactor | Engineering | 2026-01-01 | 2026-12-31 | 1
API Gateway Migration | Engineering | 2026-04-01 | 2027-03-31 | 2
Mobile SDK 3.0 | Engineering | 2026-07-01 | 2027-06-30 | 3
Onboarding Redesign | Product | 2026-01-01 | 2026-06-30 | 4
Pricing Page A/B | Product | 2026-04-01 | 2026-09-30 | 5
Self-Serve Trial Flow | Product | 2026-04-01 | 2027-03-31 | 6
Q2 Brand Refresh | Marketing | 2026-01-01 | 2026-06-30 | 7
Annual Conference | Marketing | 2026-07-01 | 2026-09-30 | 8
ABM Pilot Cohort | Marketing | 2026-04-01 | 2027-06-30 | 9
SOC2 Type II Audit | Operations | 2026-01-01 | 2026-12-31 | 10
Vendor Consolidation | Operations | 2026-04-01 | 2027-03-31 | 11

## Milestones
Activity | Milestone Date | Milestone Type | Milestone Label | Label Position
Auth Service v2 | 2026-02-15 | Major | Design review | R
Auth Service v2 | 2026-03-10 | Minor | Code freeze | L
Auth Service v2 | 2026-03-28 | Major | GA | R
Data Pipeline Refactor | 2026-02-28 | Minor | Schema lock | R
Data Pipeline Refactor | 2026-06-15 | Major | Cutover | R
Data Pipeline Refactor | 2026-11-30 | Major | Decommission old | L
API Gateway Migration | 2026-05-20 | Minor | Canary 10% | R
API Gateway Migration | 2026-09-15 | Major | 100% traffic | R
API Gateway Migration | 2027-02-28 | Major | Legacy gateway off | R
Mobile SDK 3.0 | 2026-09-10 | Minor | Beta release | R
Mobile SDK 3.0 | 2027-04-20 | Major | GA | R
Onboarding Redesign | 2026-03-01 | Major | Live to 100% | R
Onboarding Redesign | 2026-05-15 | Minor | Iteration 2 | R
Pricing Page A/B | 2026-08-05 | Major | Winner declared | R
Self-Serve Trial Flow | 2026-07-20 | Minor | MVP | R
Self-Serve Trial Flow | 2026-12-10 | Major | Public launch | R
Self-Serve Trial Flow | 2027-02-28 | Major | Conversion target met | L
Q2 Brand Refresh | 2026-05-01 | Major | Site live | R
Annual Conference | 2026-09-22 | Major | Day 1 keynote | R
ABM Pilot Cohort | 2026-09-01 | Minor | Wave 1 launch | R
ABM Pilot Cohort | 2027-03-15 | Major | Renewal target | R
SOC2 Type II Audit | 2026-04-01 | Minor | Evidence collection | R
SOC2 Type II Audit | 2026-11-15 | Major | Report received | R
Vendor Consolidation | 2026-01-01 | __phantom |  | none